Rotary Projects Timor-Leste East

June 2025 Work Program

Project Scope

Installation of SkyHydrant water filter systems of up to 10 schools in Timor Leste including:

SCHOOL NAMES & DETAILS

| · Location Name; Town/Village; Total; SH Type; Delivered; Name. Los Palos High School (1) Lere; Los Palos; 1000; Max; TBC; RC Sandy Bay #2. Halico Orphanage; Halico; 400; Gem; TBC; RC Herission. Baucau Primary School; Baucau; 1500; Max; TBC; RC Esperance Bay. Sisters Baucau Ursulin; Baucau; 1500; Max; TBC; RC Bunbury. Oeussi; Oeussi; 1500; Max; TBC; TBC Philip Island San Remo. Oeussi; Oeussi; 1500; Max; TBC; TBC RC Sale. Number 5 Primary School; Comoro; 2500; Max; TBC; TBC RC Sale. Alma Sisters; Comoro; 500; Gem; TBC; TBC RC Sale. Primary School Baucau; Baucau; 200; Gem; TBC; TBC RC Sale & Koo Wee Rup Lang Lang. Suai Rehabilitation Center SSPS Sister; Suai; 300; Gem; TBC; Joan & Duncan Fell & RC Longford. Public School number 1 baucau; Baucau; 2,000; Max; TBC; TBC RC Launceston. Public School Number 2 Baucau; Baucau; 2,500; Max; TBC; TBC Ken Harris. Escola Tecnica Los Palos; Los Palos; 500; Gem; TBC; RC Byford & The 2/2nd Commando Foundation. TBC; TBC; RC Leongatha. TBC; TBC; RC Boronia. TBC; TBC; RC Casey. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project will be carried out under the RAWCS Project 21-2011-12 Project Participants & Sponsors As follows: Project Participants · RPTLE – Project lead; project coordination and management · Don Bosco Training Center - Community needs assessment; filter system installations; follow-up & support · Rotary Club of Greater Bunbury – provision of volunteers for installations in Timor-Leste · Rotary Club of Longford - provision of volunteers for installations in Timor-Leste plus Two members of Bunnings Darwin - Rotary Clubs of Kwinana & Albany Port provision of volunteers for installations in Timor-Leste Project Sponsors: · Disaster Aid Australia – Sponsor of 10 SkyHydrant Water Filters · Rotary Club of Greater Bunbury - $10,000 · Rotary Club of Longford - $15,000 · RPTLE $15,000 3. Project Delivery Team Team Members: · Project Manager – Max Bird · Don Bosco Director – Brother Adriano · Installation Team – Technicians provided by Don Bosco Training Center · Rotary Volunteers – TBC (5 per team?) Numbers and names still to be confirmed by the clubs Project Vehicles Two support vehicles provided in-country by RPTLE (1) and Don Bosco (1) 4. Project Schedule Project will be carried out in June 2025 either using 2 or 3 volunteer teams However, the number of installation sites ready to proceed will determine either option Will confirm with Brother Adriano, but would like at least six sites ready for Installation. Group 1 Arrive Timor Leste Sunday, 1 June; depart Tuesday 10 June (10 working days); Number of installations 2-3 /Schools to be confirmed from the above list as to who is ready, working toward Los Palos East of Dili; volunteers from Bunbury Group 2 Arrive Timor Leste Monday 9th June; depart Thursday 19th June (10 working days); Number of installations 2-3 /Schools to be confirmed from the above list as to who is ready, working toward Halico West of Dili; volunteers from Longford including two members from Bunnings Darwin Group 3 Arrive Timor Leste Wednesday 18th June; depart Saturday 28th June (10 working days); Number of installations/Schools/Area; volunteers from. (Still needs to be confirmed we have the numbers they may be members of the Rotary Club of Kwinana and Albany Port) - Pending Tasks - Confirm budget - Confirm recipient schools are prepared for installations - Confirm Rotary volunteer team members - Project will be carried out under the RAWCS Project 21-2011-12 2. Project Participants & Sponsors As follows: Project Participants - RPTLE – Project lead; project coordination and management - Don Bosco Training Center - Community needs assessment; filter system installations; follow-up & support - Group 1: Rotary Club of Greater Bunbury – provision of volunteers for installations in Timor Leste - Group 2: Rotary Club of Longford - provision of volunteers for installations in Timor Leste Plus Two Members of the Bunnings Team from Darwin - Group 3: Rotary Clubs of Kwinana & Albany Port provision of volunteers for installations in Timor Leste Pending Tasks - Confirm recipient schools are prepared for installations, (Brother Adrino) - Confirm Rotary volunteer team members (Rotary Clubs Bunbury & Longford and Kwinana) - Confirm Team members from Bunnings Darwin. |  |  |  |  |  |
| Please Confirm Rotary volunteer team members Rotary Club of Greater Bunbury - David Castro - TBC - TBC - TBC - TBC |  |  |  |  |  |
| Rotary Club of Longford and Bunnings Darwin |  |  |  |  |  |
| - Teena McLaren Bird - Michael Bird - Tashh Granucci - TBC - TBC Rotary Club of Kwinana & Albany Port - Chis Iriks - John Iriks - Mal Dodson - Ian Critchly - TBC Please note once I have the confirmed numbers of people traveling, I will then open the Rotary Australia Worldwide Community Service: (RAWCS) portal to the nominated people to register on line this will then cover all the people concerned with Rotary Travel Insurance I will then need an email address for each person traveling or working on the project, please note couples cannot share a common email address RAWCS: will also require the following (once I open the portal) - Fill in the Application Form - Read the Agreement, Release & Waiver of Liability: - Agree to the Code of Conduct: - Signature Form: (Done automatically) - Medical Certificate: (There will be a certificate generated by the system for the Doctor to sign) - Child Protection: (Working with Children Card or a National Police Clearance not less than 6 months old) |  |  |  |  |  |
| Yours Truely -- Max Bird Project Manager Rotary Projects Timor-Leste East M: 0419045835 ¦ E: maxbird@bigpond.com 233 Lambeth Circle Wellard WA 6167 Rotary Australia World Community Service (RAWCS) |  |  |  |  |  |